## Sprint Velocity
Sprint | Points Committed | Points Completed | Velocity % | Carryover
Sprint 22 | 34 | 31 | 91% | 3
Sprint 23 | 38 | 35 | 92% | 3
Sprint 24 | 40 | 28 | 70% | 12
Sprint 25 | 36 | 36 | 100% | 0
Sprint 26 | 42 | 39 | 93% | 3
Sprint 27 | 35 | 33 | 94% | 2
Sprint 28 | 44 | 41 | 93% | 3
Sprint 29 | 38 | 38 | 100% | 0
Sprint 30 | 40 | 37 | 93% | 3
Sprint 31 | 45 | 30 | 67% | 15

## Bug Backlog
ID | Title | Severity | Status | Days Open | Assigned To
BUG-401 | PDF conversion hangs on encrypted files | Critical | In Progress | 3 | Alice
BUG-402 | XLSX multi-sheet output loses formatting | High | Open | 12 | Unassigned
BUG-403 | Memory spike on files larger than 50MB | High | Open | 8 | Bob
BUG-404 | CSV delimiter auto-detection fails for tabs | Medium | In Progress | 5 | Charlie
BUG-405 | PPTX speaker notes not extracted | Low | Open | 30 | Unassigned
BUG-406 | HTML table borders lost in markdown output | Medium | Fixed | 2 | Alice
BUG-407 | Timeout not configurable via CLI flag | Medium | Open | 15 | Unassigned
BUG-408 | Unicode filenames cause crash on Windows | High | Open | 7 | Dave

## Team Allocation
Team Member | Role | Current Sprint Focus | Availability %
Alice | Senior Engineer | Bug fixes + code review | 80%
Bob | Engineer | Performance optimization | 100%
Charlie | Engineer | CSV/TSV converter rewrite | 60%
Dave | Engineer | Windows compatibility | 100%
Eve | QA Lead | Test automation framework | 90%